## Attendance
Date | Nick | Danny | Theo | Phillip | Sam | Steve
2020-01-30 | [6 empty] | Green = Attendance
2020-02-05 | [6 empty] | Yellow = Reason Given
2020-02-11 | [6 empty] | Red = No show
2020-02-19 | [6 empty] | WFH = Work from home
2020-02-24
2020-02-25 |  |  | WFH
2020-02-27

## Agile Scrum Plan
Agile Scrum Plan
Date/Time | Scrum | Retrospect | Sprint Review | Project Owner
Week 4/ Jan |  |  |  | Scrum Master
Week 1/Feb |  |  |  | Team Member
Week 2/ Feb | Started research on FSM
Started generating pseudocode
Week 3/ Feb | Created FSM
Created rules for FSM
Started report
Week 4/ Feb
Week 1/Mar
Week 2/ Mar
Week 3/ Mar
Week 4/ Mar
Demonstration Week

## Gantt Chart
Project Step | Week 4 January | Week 1 Februray | Week 2 February | Week 3 February | Week 4 February | Week 1 March | Week 2 March | Week 3 March | Week 4 March | Due 27/03
Research and Development
Generating Pseudocode
Class Design
Designing the Finite State
Creating the Finite State
Implementing the Finite State
Testing
Writeup