## Attendance
Date | Nick | Danny | Theo | Phillip | Sam | Steve
2020-01-30 | [6 empty] | Green = Attendance
2020-02-05 | [6 empty] | Yellow = Reason Given
2020-02-11 | [6 empty] | Red = No show
2020-02-19 | [6 empty] | WFH = Work from home
2020-02-24
2020-02-25 |  |  | WFH
2020-02-27
2020-02-28

## Agile Scrum Plan
Agile Scrum Plan
Date/Time | Scrum | Retrospect | Sprint Review | Project Owner |  | Retrospect = Did we do it
Week 4/ Jan | Started research on FSM | Yes | We successfully researched FSM using different sources and Looked at multiple strategies of implementation | Scrum Master | Nick | Sprint review = How well did we do it and what could be better
| Started planing scrum plan | Yes | We colour coded each week to correctly divide the different parts of the assignment plan, found no issues
Week 1/Feb | Started generating pseudocode | Yes | We created a lot of pseudocode for the FSM states, which we can now impliment into the project | Team Member | Sam
Week 2/ Feb | Created rules for FSM | Yes | Created rules for each of the states and the varying types of tanks |  | Steve
| Started report | Yes | We started the introduction with the explanation of the FSM with also the project management |  | Phil
Week 3/ Feb | Create OOP FSM
Week 4/ Feb
Week 1/Mar
Week 2/ Mar
Week 3/ Mar
Week 4/ Mar
Demonstration Week
Create Scrum plan
Nike-sh
Steve

## Gantt Chart
Project Step | Week 4 January | Week 1 Februray | Week 2 February | Week 3 February | Week 4 February | Week 1 March | Week 2 March | Week 3 March | Week 4 March | Due 27/03
Research and Development
Generating Pseudocode
Class Design
Designing the Finite State
Creating the Finite State
Implementing the Finite State
Testing
Writeup