## Attendance
Date | Nick | Danny | Theo | Phillip | Sam | Steve
2020-01-30 | [6 empty] | Green = Attendance
2020-02-05 | [6 empty] | Yellow = Reason Given
2020-02-11 | [6 empty] | Red = No show
2020-02-19 | [6 empty] | WFH = Work from home
2020-02-24
2020-02-25 |  |  | WFH
2020-02-27
2020-02-28
2020-03-06

## Agile Scrum Plan
Agile Scrum Plan
Date/Time | Scrum | Retrospect | Sprint Review | Project Owner |  | Retrospect = Did we do it
Week 4/ Jan | Started research on FSM | Yes | We successfully researched FSM using different sources and Looked at multiple strategies of implementation | Scrum Master | Nick | Sprint review = How well did we do it and what could be better
| Started planing scrum plan | Yes | We colour coded each week to correctly divide the different parts of the assignment plan, found no issues
Week 1/Feb | Started generating pseudocode | Yes | We created a lot of pseudocode for the FSM states, which we can now impliment into the project | Team Member | Sam
Week 2/ Feb | Created rules for FSM | Yes | Created rules for each of the states and the varying types of tanks |  | Steve
| Started report | Yes | We started the introduction with the explanation of the FSM with also the project management |  | Phil
Week 3/ Feb | Create OOP FSM
Week 4/ Feb
Week 1/Mar
Week 2/ Mar
Week 3/ Mar
Week 4/ Mar
Demonstration Week
Create Scrum plan
Nike-sh
Steve

## Gantt Chart
Project Step | Week 4 January | Week 1 Februray | Week 2 February | Week 3 February | Week 4 February | Week 1 March | Week 2 March | Week 3 March | Week 4 March | Due 27/03
Research and Development
Generating Pseudocode
Class Design
Designing the Finite State
Creating the Finite State
Creating Idle State
Create Patrol State
Create Attack Enemy State
Create Find Cover State
Create Collect Consumables State
Create Defend Base State
Implementing the Finite State
Testing
Writeup